## Sheet1
WINGS TEAM
Testing Schedule
| Great Date | 2015-05-10
Duration
| Test Lead | Quyen Nguyen
| Greator | Quyen Nguyen
| Purpose | To show schedule of my team on test phase.
|  | Date | Team Meeting to prepare test plan and training how to write test cases for team member .
|  | Milestone Task | Human Resource | Start Date | Delivery Date

## Incremental 1
Testing Schedule For Incremetal 1
Task | Member | Description | Assign | Start Date | End Date | Constraint
Write test plan | Quyen Nguyen |  | Quyen Nguyen | 24/10/2015 | 28/10/2015
Draw test process | Quyen Nguyen | Define all level of test will be performed and draw test process. | Quyen Nguyen | 25/10/2015 | 25/10/2015
Update Test plan 1st | Quyen Nguyen | After we get requirement from customers, base on Architecture Driver Specification document, Quyen Nguyen as a Test Leader , She will prepare and review the last time all template, define function will be tested and show template for members. | Quyen Nguyen | 2015-04-11 | 2015-05-11 | > 2hour/day
Update Test plan 2nd | Quyen Nguyen |  | Quyen Nguyen | 24/11/2015 | 24/11/2015
Update Test plan 3rd | Quyen Nguyen | Design all quality attribute test cases | Quyen Nguyen | 2015-01-12 | 2015-03-12
Research manage bugs tool for test : Bug zilla | Quyen Nguyen | Research and get knowledge about BugsZilla to control bugs in test phase. | Quyen Nguyen | 15/12/2015 | 30/12/2015 | > 1hour/day
Training how to write test case | Quyen Nguyen | Team meeting to train team members can be understand to write test case. ( System test case) | Quyen Nguyen | 22/12/2015 | 22/12/2015 | ~ 3 hour/day
Training how to write test case | Quyen Nguyen | Review example test case which are written by team members and fix to make they have a knowledge clearly about design test case. | Quyen Nguyen | 22/12/1015 | 22/12/2015 | 1 hour
| Quyen Nguyen | Break task for team member write System test case, each member will write 2 main function but Danh Nguyen is 1. Because He have a lot of task for Architecture Phase, it spent him a lot of time, so to ensure that he can trade- off his time and complete his task, I only assign for him write 1 function. | Quyen Nguyen | 26/1/2016 | 28/1/2016 | ~ 1h30p
| Quyen Nguyen | Basic Management | Thanh Tran | 26/1/2016 | 28/1/2016 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
| Quyen Nguyen | Manage restaurant 's account & Manage customer 's account | Quyen Nguyen | 26/1/2016 | 28/1/2016 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
| Quyen Nguyen | Manage Advertisement | Son Do | 26/1/2016 | 28/1/2016 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
| Quyen Nguyen | Manage Promotion | Danh Nguyen | 26/1/2016 | 28/1/2016 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
| Quyen Nguyen | Manage Campaign | Phu Hoang | 26/1/2016 | 28/1/2016 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
Write Qualities Attribute test cases | Quyen Nguyen |  | Quyen Nguyen | 21/10/2015 | 21/10/2015 | Spent least 3 hour to write all 10 qualities attribute.
Perform Qualities Attribute test cases | Quyen Nguyen |  | Quyen Nguyen | 16/1/2016 | 16/1/2016
Research Junit | Quyen Nguyen | How to apply Junit on java eclipse | Thanh Tran & Son Do | 16/12/2015 | 30/12/2015 | > 1hour/day
Research Jmeter | Quyen Nguyen | How to use Jmeter to test performance of system | Danh Nguyen | 16/12/2015 | 30/12/2015 | > 1 hour/day
Deadline always at : 23h59pm of that day.
Submit to control : skype : yunguyen1210
Submit the final of your task : skype: yunguyen1210
The final Testcase document will be summarize and update on Dropbox : Restaurant Guys folder
For member who is assigned research Bugs Zilla, Jmetter , Junit : All knowledge that you got will be present for team member at the next team meeting.

## Incremental 2
Testing Schedule For Incremetal 2
Task | Member | Description | Assign | Start Date | End Date | Constraint
Break task for team member to write Acceptance test case | Quyen Nguyen | Break task for team member write System test case, each member will write 2 main function but Danh Nguyen is 1. Because He have a lot of task for Architecture Phase, it spent him a lot of time, so to ensure that he can trade- off his time and complete his task, I only assign for him write 1 function. | Quyen Nguyen | 2016-04-04 | 2016-05-04 | ~ 1h30p
Write test case for FR1 | Quyen Nguyen | Upload Image | Thanh Tran | 2016-04-04 | 2016-05-04 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
Write test case for FR2 & FR4 | Quyen Nguyen | Manage Profile of restaurant | Quyen Nguyen | 2016-04-04 | 2016-05-04 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
Write test case for FR2 & FR4 | Quyen Nguyen | View infromation of App | Son Do | 2016-04-04 | 2016-05-04 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
Write test case for FR2 & FR4 | Quyen Nguyen | Search information of app | Danh Nguyen | 2016-04-04 | 2016-05-04 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
Write test case for FR2 & FR4 | Quyen Nguyen | Manage Profile of app | Phu Hoang | 2016-04-04 | 2016-05-04 | Each day, member should spend 2 hour to try to write at least 2 test case for this main Function after finished, member will send to Testing Leader through skype this file to make Testing leader can control the progress.
Write intergration test case | Quyen Nguyen |  | Phu Hoang | 31/3/2016 | 2016-01-04 | Spent least 3 hour to write intergration test case
Deadline always at : 23h59pm of that day.
Submit to control : skype : yunguyen1210
Submit the final of your task : skype: yunguyen1210
The final Testcase document will be summarize and update on Dropbox : Restaurant Guys folder
For member who is assigned research Bugs Zilla, Jmetter , Junit : All knowledge that you got will be present for team member at the next team meeting.